## Matrix
Document Requirements Matrix - Example Project
Y = required in that phase. Keep the Code column formatted as Text (2.10 is not 2.1).
Code | Title | Allowed Types | Phase 1 - Tender | Phase 2 - Design | Phase 3 - Construction | Phase 4 - Handover | Notes
1 | General & Administration
1.1 | Contractor Information Form | .pdf; .docx | Y | Y | Y | Y
1.2 | Insurance Certificates | .pdf | Y | Y | Y | Y
1.3 | Health & Safety Policy | .pdf; .docx | Y | Y | Y
1.4 | Quality Management Plan | .pdf; .docx | Y | Y | Y
2 | Design
2.1 | Design Basis Report | .pdf; .docx | Y | Y
2.2 | Architectural Drawings | .pdf; .dwg |  | Y | Y
2.3 | Structural Calculations | .pdf; .xlsx |  | Y | Y
2.4 | Structural Drawings | .pdf; .dwg |  | Y | Y
2.5 | Mechanical Design Report |  |  | Y
2.6 | Electrical Design Report |  |  | Y
2.7 | Plumbing & Drainage Design |  |  | Y
2.8 | Fire Strategy Report | .pdf |  | Y | Y
2.9 | Geotechnical Report | .pdf |  | Y
2.10 | Design Risk Register | .xlsx; .pdf |  | Y | Y
2.11 | Design Change Log | .xlsx |  | Y | Y | Y
3 | Planning & Permits
3.1 | Planning Application | .pdf | Y | Y
3.2 | Building Regulations Approval | .pdf |  | Y | Y
3.3 | Environmental Impact Assessment | .pdf |  | Y
3.4 | Utility Connection Agreements | .pdf |  |  | Y
3.5 | Road Closure Permits | .pdf |  |  | Y
4 | Procurement
4.1 | Procurement Strategy |  | Y | Y
4.2 | Subcontractor List | .xlsx; .pdf |  | Y | Y
4.3 | Long-lead Items Schedule | .xlsx |  | Y | Y
4.4 | Material Submittals |  |  |  | Y
4.5 | Supplier Warranties | .pdf |  |  | Y | Y
4.6 | Purchase Order Log | .xlsx |  |  | Y
5 | Construction
5.1 | Construction Programme | .pdf; .mpp; .xlsx | Y |  | Y
5.2 | Method Statements | .pdf; .docx |  |  | Y
5.3 | Site Logistics Plan | .pdf |  |  | Y
5.4 | Daily Site Diaries |  |  |  | Y
5.5 | Monthly Progress Reports | .pdf |  |  | Y
5.6 | Temporary Works Register | .xlsx |  |  | Y
5.7 | Site Photographs | .jpg; .png; .zip |  |  | Y | Y
5.8 | Variations Register | .xlsx |  |  | Y | Y
6 | Health, Safety & Environment
6.1 | Health & Safety Plan | .pdf; .docx | Y | Y | Y
6.2 | Risk Assessments |  |  | Y | Y
6.3 | COSHH Register | .xlsx; .pdf |  |  | Y
6.4 | Environmental Management Plan | .pdf |  | Y | Y
6.5 | Site Waste Management Plan | .pdf |  |  | Y
6.6 | Incident Log | .xlsx |  |  | Y | Y
6.7 | Site Induction & Training Records |  |  |  | Y
7 | Quality Assurance
7.1 | Inspection & Test Plan | .pdf; .xlsx | Y | Y | Y
7.2 | Material Test Certificates | .pdf |  |  | Y | Y
7.3 | Non-conformance Register | .xlsx |  |  | Y | Y
7.4 | Quality Audit Reports | .pdf |  |  | Y
7.5 | Snagging List | .xlsx; .pdf |  |  |  | Y
7.6 | Quality Records Index | .xlsx |  |  |  | Y
8 | Testing & Commissioning
8.1 | Commissioning Plan | .pdf |  |  | Y
8.2 | Electrical Test Certificates | .pdf |  |  |  | Y
8.3 | Mechanical Commissioning Records | .pdf |  |  |  | Y
8.4 | Fire Alarm Certificate | .pdf |  |  |  | Y
8.5 | Witness Test Reports | .pdf |  |  |  | Y
9 | Handover & Close-out
9.1 | As-built Drawings | .pdf; .dwg |  |  |  | Y
9.2 | O&M Manuals | .pdf |  |  |  | Y
9.3 | Health & Safety File | .pdf |  |  |  | Y
9.4 | Building Log Book | .pdf |  |  |  | Y
9.5 | Asset Register | .xlsx |  |  |  | Y
9.6 | Warranties & Guarantees | .pdf |  |  |  | Y
9.7 | End-user Training Records | .pdf |  |  |  | Y
9.8 | Practical Completion Certificate | .pdf |  |  |  | Y
9.9 | Final Account | .pdf; .xlsx |  |  |  | Y

## How to use
How this matrix is read by FileCrawler
- The header row needs a 'Code' column. Title and Allowed Types are optional.
- Every other column with Y/N marks is a phase. Y, Yes, X, R or 1 = required; blank, N or - = not.
- Codes must be numeric (1.1, 2.11). Format the Code column as Text: as numbers, 2.10 becomes 2.1.
- A row whose code has no dot (e.g. '2') and no Y marks is a category heading.
- Allowed Types: e.g. '.pdf; .docx'. Leave blank to accept any file type.
- The submission's folders must START with the code, e.g. '2.10 Design Risk Register'.
- Rows and columns above the header (titles, notes) are ignored.